## Sheet1
Sprint ID | User Story | Task Item | Responsible | Status | Hours/ day for each sprint iteration | [5 empty] | Sprint Review
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6
1 | As a product owner I want the device to receives signal and turn on/ off the light | Wire Bluetooth device and motor into processor chipset | Jang Soon Myun | Done | 2 | 2 | 3 |  |  |  | 12
|  | Configuring the motor movement | Park Geon O | Done |  |  | 2 | 2 | 3
|  | Configuring the Bluetooth frequency and ID | Park Geon O | Done |  |  | 2 | 3 | 2
|  | Program the processor to receive certain command | Jang Soon Myun | Done |  |  |  | 4 | 3 | 4
|  | Change the frame design to fit desireable switch | Jang Soon Myun | Ongoing |  |  |  |  | 1 | 1
2 | As a product owner I want the Android application to send and collect data using Bluetooth | Create a function for identify the device's Bluetooth | Andrew Sebastian | Ongoing | 2 | 2 |  |  |  |  | 10
|  | Create a function for opening stream I/O operation | Andrew Sebastian | Ongoing |  | 3 | 4
|  | Create a function to receives current device state | Andrew Sebastian | Planned |  |  | 3
|  | Create a logic implementation for data manipulation | Andrew Sebastian | Planned |  |  |  | 4 | 4 | 4
3 | As a product owner I want the application to have user friendly interface | Design the data flow as the standard for user interaction | Jin Kwang Un | Planned | 2 | 2 |  |  |  |  | 6
|  | Implement the user Interface | Jin Kwang Un | Planned |  | 4 | 4 | 3
4 | As an user I want my apllication to automatically using Bluetooth | Indicate service when application start | Vincent Kelly | Planned | 3 | 4 |  |  |  |  | 5
|  | Gain user runtime permission to run Bluetooth | Vincent Kelly | Planned |  |  | 2 | 2
5 | As an user I want to schedule light life-time | Create a function to measure the running time of a light | Jang Soon Myun | Planned | 3 | 3 |  |  |  |  | 5
|  | Create a function to send change signal on designate time | Jang Soon Myun | Planned |  |  | 3 | 2
6 | As a product owner I want the device to also support WIFI capabilities | Wire WIFI transmitter and receiver to current device | Park Geon O | Planned | 3 | 3 | 3 |  |  |  | 10
|  | Configuring the WIFI frequency and ID | Park Geon O | Planned |  |  | 3 | 2
|  | Program the processor to identify WIFI signal and translates it | Andrew Sebastian | Planned |  |  |  | 4 | 3 | 4
7 | As a product owner I want the application to send and collect data with WIFI | Gain user runtime permission to run WIFI | Hassan | Planned | 2 | 2 |  |  |  |  | 10
|  | Create a function for opening stream I/O operation(WIFI-based) | Hassan | Planned |  |  | 3 | 4
|  | Create WIFI signal data manipulation | Jin Kwang Un | Planned |  |  |  | 2 | 4 | 4