## Sheet1
ID | Summary | Planned For | Found By | Severity | Priority | Estimate Time | Severity Levels | Priority Levels
D01 | The device doesn't fit every switch | Sprint 1 | Jang Soon Myun | Unclassified | Low | 5 | Unclassified | Unassigned
| The device is non-attachable | Sprint 1 | Jang Soon Myun | Normal | Medium | 2 | Normal | Low
| The device can't synchronize with the bluetooth smoothly. | Sprint 2 | Andrew Sebastian | Blocker | Major | 1 | Major | Medium
| A insufficient power supply to device | Sprint 1 | Jang Soon Myun | Major | Medium | 3 | Critical | Major
| A weak frame of prototype version | Sprint 1 | Jang Soon Myun | Normal | Low | 7 | Blocker

## Sheet2
The variety shape of switches were discovered.
There was troublesomed to attach on the switch
A transmission speed wasn't same between the microprocessor and the bluetooth.
Low power in the battery
The frame is made by styrofoam